## Test Plan
Please Click Here to show my testplan full PDF.

## Test Scenarios
Project Name | Bangladesh Railway E-Ticketing Service
Reference Document | FRS
Created By | Md.Mostafizur Rahman Zahid
Creation Date | 26-03-2026
Approval Date | 28-03-2026
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 | Home | Verify website URL accessibility across supported browsers | P0 | 3
TS_002 | Home | Verify the functionality of "From Station" dropdown field | P1 | 8
TS_003 | Home | Verify the functionality of "To Station" dropdown field | P1 | 8
TS_004 | Home | Verify the functionality of "Date of Journey" field | P1 | 10
TS_005 | Home | Verify the functionality of "Choose Class" dropdown field | P2 | 5
TS_006 | Home | Verify the functionality of "Search Trains" button | P0 | 6
TS_007 | Home | Verify train search functionality with valid input data | P0 | 5
TS_008 | Home | Verify train search functionality with invalid or empty input data | P1 | 8
TS_009 | Register | Verify the NID verification registration page UI elements | P2 | 3
TS_010 | Register | Verify the functionality of "Full Name" field in NID section | P1 | 10
TS_011 | Register | Verify the functionality of "Mobile Number" field in NID section | P1 | 12
TS_012 | Register | Verify the functionality of "NID Number" field | P1 | 10
TS_013 | Register | Verify the functionality of "Date of Birth" field in NID section | P1 | 8
TS_014 | Register | Verify reCAPTCHA functionality during registration | P0 | 4
TS_015 | Register | Verify the functionality of "Verify" button | P0 | 5
TS_016 | Register | Verify the functionality of "Submit Data" button | P1 | 4
TS_017 | Register | Verify the registration form UI after successful verification | P2 | 3
TS_018 | Register | Verify the functionality of "Full Name" field in registration form | P1 | 10
TS_019 | Register | Verify the functionality of "E-mail" field | P1 | 15
TS_020 | Register | Verify the functionality of "Mobile Number" field in registration form | P1 | 10
TS_021 | Register | Verify the functionality of "Confirm Mobile" field | P1 | 8
TS_022 | Register | Verify the functionality of "Identification Type" dropdown field | P2 | 5
TS_023 | Register | Verify the functionality of "Identification Number" field | P1 | 8
TS_024 | Register | Verify the functionality of "Post Code" field | P1 | 8
TS_025 | Register | Verify the functionality of "Date of Birth" field in registration form | P1 | 8
TS_026 | Register | Verify the functionality of "Address" field | P2 | 6
TS_027 | Register | Verify the functionality of "New Password" field | P0 | 15
TS_028 | Register | Verify the functionality of "Confirm Password" field | P0 | 10
TS_029 | Register | Verify password visibility toggle functionality | P3 | 2
TS_030 | Register | Verify the functionality of file upload feature | P1 | 12
TS_031 | Register | Verify supported file formats for upload functionality | P1 | 6
TS_032 | Register | Verify file size restriction during file upload | P2 | 4
TS_033 | Register | Verify the functionality of "Sign Up" button | P0 | 5
TS_034 | Register | Verify user registration with valid input data | P0 | 3
TS_035 | Register | Verify user registration with invalid input data | P1 | 12
TS_036 | Register | Verify the functionality of "Already Registered?" link | P3 | 2
TS_037 | Login | Verify the login page UI elements | P3 | 2
TS_038 | Login | Verify the functionality of "Mobile Number" field in login page | P1 | 8
TS_039 | Login | Verify the functionality of "Password" field in login page | P1 | 8
TS_040 | Login | Verify successful login with valid credentials | P0 | 3
TS_041 | Login | Verify unsuccessful login with invalid credentials | P1 | 8
TS_042 | Login | Verify validation messages for empty login fields | P1 | 5
TS_043 | Login | Verify the functionality of "Forgot Password" feature | P1 | 8
TS_044 | Login | Verify the functionality of "Need Help" option | P3 | 2
TS_045 | Train Information | Verify train information page accessibility | P2 | 2
TS_046 | Train Information | Verify train search functionality from train information page | P1 | 5
TS_047 | Train Information | Verify train details display after successful search | P1 | 5
TS_048 | Contact Us | Verify the functionality of refund contact information | P3 | 2
TS_049 | Contact Us | Verify the functionality of support email | P3 | 2
TS_050 | Contact Us | Verify the functionality of Terms & Conditions page | P3 | 2
TS_051 | Contact Us | Verify the functionality of Privacy Policy page | P3 | 2
TS_052 | Contact Us | Verify hotline number visibility and accessibility | P3 | 4
TS_053 | General | Verify website responsiveness across multiple devices | P2 | 6
TS_054 | General | Verify cross-browser compatibility | P1 | 5
TS_055 | General | Verify session timeout functionality | P2 | 3
TS_056 | General | Verify error message handling throughout the application | P1 | 10
TS_057 | General | Verify website page loading performance | P2 | 3
TS_058 | General | Verify secure transmission of user data | P0 | 3
TS_058 | General | Validate secure transmission of user data | P0 | 3

## TestCase
Product Name |  | BD Railway E-Ticketing Service | TC Start Date | 26/03/2026 | TC Execution Start Date | - - |  |  |  |  | TEST CASE
Module Name |  | Account | TC End Date | 28/03/2026 | TC Execution End Date | - - |  |  |  |  | PASS | 35
Epic |  |  | Test Case Developed By | Md.Mostafizur Rahman Zahid | Browser (tested) | Yes |  |  |  |  | FAIL | 5
Developer Name (TL) |  |  | Test Case Reviewed By | Rubel Hosain | Performance (tested) | Yes |  |  |  |  | NO RUN | 0
Test Executed by |  | Md. Mostafizur Rahman Zahid | [8 empty] | BLOCKED | 0
[11 empty] | TOTAL | 40
#SL | Module | Type of Testing | Features | Test Cases | Expected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screenshot | Dev Comments | Final Status | Remarks
1 | Home | Functional Testing | URL Accessibility | Opening website URL in supported browsers | Website should open successfully in all supported browsers | Found as per expectation | Chrome, Firefox, Edge | 1. Open browser 2. Enter website URL | N/A | N/A | Passed
2 | Home | Functional Testing | From Station | Selecting valid departure station | System should display selected departure station | Found as per expectation | Dhaka | 1. Open Home page 2. Select From Station | N/A | N/A | Passed
3 | Home | Functional Testing | To Station | Selecting valid destination station | System should display selected destination station | Found as per expectation | Chittagong | 1. Select To Station | N/A | N/A | Passed
4 | Home | Functional Testing | Date of Journey | Selecting valid journey date | System should allow valid date selection | Found as per expectation | 25-06-2026 | 1. Open calendar 2. Select journey date | N/A | N/A | Passed
5 | Home | Functional Testing | Search Trains | Searching trains with valid data | System should display available train list | Found as per expectation | Dhaka → Chittagong | 1. Fill journey information 2. Click Search Trains | N/A | N/A | Passed
6 | Home | Functional Testing | Search Trains | Searching trains with empty mandatory fields | System should show validation message | Found as per expectation | None | 1. Keep fields blank 2. Click Search Trains | N/A | N/A | Passed
7 | Register | Functional Testing | Full Name | Keeping full name field blank | System should show required field validation | Found as per expectation | None | 1. Open registration page 2. Keep Full Name blank | N/A | N/A | Passed
8 | Register | Functional Testing | Full Name | Entering numeric values in full name field | System should reject numeric values | Found not as per expectation | 12345 | 1. Enter numeric value in Full Name field | Name validation bug | N/A | Failed
9 | Register | Functional Testing | Full Name | Entering special characters in full name field | System should reject special characters | Found not as per expectation | @#$%^ | 1. Enter special characters in Full Name field | Special character validation issue | N/A | Failed
10 | Register | Functional Testing | Mobile Number | Entering valid 11-digit mobile number | System should accept valid mobile number | Found as per expectation | 1712345678 | 1. Enter valid mobile number | N/A | N/A | Passed
11 | Register | Functional Testing | Mobile Number | Entering alphabets in mobile number field | System should reject alphabetic input | Found as per expectation | abcdef | 1. Enter alphabets in Mobile Number field | N/A | N/A | Passed
12 | Register | Functional Testing | NID Number | Entering valid NID number | System should accept valid NID number | Found as per expectation | 1999999999999 | 1. Enter valid NID number | N/A | N/A | Passed
13 | Register | Functional Testing | Date of Birth | Opening month dropdown from DOB calendar | System should display all 12 months | Found not as per expectation | N/A | 1. Open DOB calendar 2. Open month dropdown | DOB month display bug | N/A | Failed
14 | Register | Functional Testing | Date of Birth | Opening year dropdown from DOB calendar | System should display complete year range | Found not as per expectation | N/A | 1. Open DOB calendar 2. Open year dropdown | DOB year limitation issue | N/A | Failed
15 | Register | Functional Testing | reCAPTCHA | Clicking verify without captcha | System should prevent verification | Found as per expectation | None | 1. Do not complete reCAPTCHA 2. Click Verify button | N/A | N/A | Passed
16 | Register | Functional Testing | E-mail | Entering valid email address | System should accept valid email address | Found as per expectation | zahid@gmail.com | 1. Enter valid email address | N/A | N/A | Passed
17 | Register | Functional Testing | E-mail | Entering invalid email format | System should show invalid email error | Found as per expectation | zahidgmail.com | 1. Enter invalid email format | Invalid email accepted | N/A | Passed
18 | Register | Functional Testing | Confirm Mobile | Entering unmatched mobile numbers | System should display mismatch validation | Found as per expectation | 01712345678 / 01812345679 | 1. Enter different mobile numbers | N/A | N/A | Passed
19 | Register | Functional Testing | Post Code | Entering valid 4-digit postcode | System should accept valid postcode | Found as per expectation | 1720 | 1. Enter valid postcode | N/A | N/A | Passed
20 | Register | Functional Testing | Post Code | Entering more than 4 digits in postcode field | System should reject postcode exceeding 4 digits | Found not as per expectation | 123456789012 | 1. Enter more than 4 digits in Post Code field | Postcode validation issue | N/A | Failed
21 | Register | Functional Testing | Password | Entering strong password | System should accept strong password | Found as per expectation | Zahid@123 | 1. Enter strong password | N/A | N/A | Passed
22 | Register | Functional Testing | Confirm Password | Entering mismatched passwords | System should display mismatch error | Found as per expectation | Zahid@123 / Zahid@321 | 1. Enter different passwords | N/A | N/A | Passed
23 | Register | Functional Testing | Password Visibility | Clicking password visibility icon | Password should become visible | Found as per expectation | None | 1. Click eye icon | N/A | N/A | Passed
24 | Register | Functional Testing | File Upload | Uploading valid JPG file | System should upload file successfully | Found as per expectation | nid.jpg | 1. Upload JPG file | N/A | N/A | Passed
25 | Register | Functional Testing | File Upload | Uploading unsupported file format | System should reject invalid file format | Found as per expectation | file.exe | 1. Upload invalid file | N/A | N/A | Passed
26 | Register | Functional Testing | Sign Up Button | Clicking sign up with valid information | User account should be created successfully | Found as per expectation | Valid registration data | 1. Fill all required fields 2. Click Sign Up | N/A | N/A | Passed
27 | Login | Functional Testing | Mobile Number | Entering registered mobile number | System should accept registered mobile number | Found as per expectation | 1712345678 | 1. Open Login page 2. Enter registered mobile number | N/A | N/A | Passed
28 | Login | Functional Testing | Password | Entering valid password | System should allow login | Found as per expectation | Zahid@123 | 1. Enter valid password 2. Click Login | N/A | N/A | Passed
29 | Login | Functional Testing | Password | Entering invalid password | System should display invalid credentials message | Found as per expectation | wrongpass | 1. Enter wrong password 2. Click Login | N/A | N/A | Passed
30 | Login | Functional Testing | Forgot Password | Clicking forgot password option | System should redirect to reset page | Found as per expectation | None | 1. Click Forgot Password | N/A | N/A | Passed
31 | Train Information | Functional Testing | Train Search | Searching train information | System should display train details | Found as per expectation | Suborno Express | 1. Search train name | N/A | N/A | Passed
32 | Contact Us | Functional Testing | Support Email | Clicking support email | System should redirect to email service | Found as per expectation | support@railway.gov.bd | 1. Click support email | N/A | N/A | Passed
33 | Contact Us | Functional Testing | Terms & Conditions | Opening Terms & Conditions page | System should display terms page | Found as per expectation | None | 1. Click Terms & Conditions | N/A | N/A | Passed
34 | Contact Us | Functional Testing | Privacy Policy | Opening Privacy Policy page | System should display privacy policy page | Found as per expectation | None | 1. Click Privacy Policy | N/A | N/A | Passed
35 | General | Compatibility Testing | Browser Compatibility | Accessing website from multiple browsers | Website should work properly in all supported browsers | Found as per expectation | Chrome, Firefox, Edge | 1. Open website in different browsers | N/A | N/A | Passed
36 | General | Compatibility Testing | Responsive Design | Opening website on mobile devices | Website should be responsive on mobile devices | Found as per expectation | Android Device | 1. Open website on mobile device | N/A | N/A | Passed
37 | General | Performance Testing | Page Loading | Opening homepage with stable internet connection | Homepage should load within acceptable time | Found as per expectation | Broadband Internet | 1. Open homepage | N/A | N/A | Passed
38 | General | Security Testing | Input Validation | Entering SQL injection payload in email field | System should block malicious SQL payload | Found as per expectation | OR 1=1-- | 1. Enter SQL payload in E-mail field | N/A | N/A | Passed
39 | General | Security Testing | Input Validation | Entering XSS payload in email field | System should block malicious script input | Found as per expectation | alert(1) | 1. Enter XSS payload in E-mail field | N/A | N/A | Passed
40 | General | Session Testing | Session Timeout | Staying inactive after login | System should expire inactive session automatically | Found as per expectation | None | 1. Login successfully 2. Stay inactive for long time | N/A | N/A | Passed

## Test Summary Report
Test Case Report | [6 empty] | Result :
Project Name | BD Railway E-Ticketing Service
Module Name | Account. |  |  |  |  | Total No. | Status
Feature Name | Register Account & Account Login.
Test Case Version | 1 |  |  |  |  | 35 | PASS
Written By | Md. Mostafizur Rahman Zahid |  |  |  |  | 5 | FAIL
Executed By | Md. Mostafizur Rahman Zahid |  |  |  |  | 0 | Not Executed | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
Reviewed By | Rubel Hosain |  |  |  |  | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 35 | 5 | 0 | 0 | 40
Grand Total | 35 | 5 | 0 | 0 | 40
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
# SL 01
Issue: Full Name field accepts numeric values.
Reproducing Steps:
1. Go to the URL https://eticket.railway.gov.bd/ 2. Open Registration page 3. Enter numeric values in Full Name field 4. Click Verify button
Env: Production.
Module: Register
Severity: P2
Full Name Numeric Validation Error
Responsible QA: Md. Mostafizur Rahman Zahid
Bug Reporting
# SL 02
Issue: Full Name field accepts special characters.
Reproducing Steps:
1. Go to the URL https://eticket.railway.gov.bd/ 2. Open Registration page 3. Enter special characters in Full Name field 4. Click Verify button
Env: Production
Module: Register
Severity: P2
Full Name Special Character Validation Error
Responsible QA: Md. Mostafizur Rahman Zahid
Bug Reporting
# SL 03
Issue: Date of Birth calendar month dropdown does not display all 12 months.
Reproducing Steps:
1. Goto the URL https://eticket.railway.gov.bd/ 2. Open Registration page 3. Click on "Select Date of Birth" 4. Open month dropdown from date picker
4. Click 'Continue'.
Env: Production.
Module: Register
Severity: P2
DOB Month Dropdown Error
Responsible QA: Md. Mostafizur Rahman Zahid
Bug Reporting
# SL 04
issue: Date of Birth calendar year dropdown shows limited year range only (2008–2014)
Reproducing Steps:
1. Goto the URL https://eticket.railway.gov.bd/ 2. Open Registration page 3. Click on "Select Date of Birth" 4. Open month dropdown from date picker
Env: Production
Module: Register
Severity: P1
DOB Year Range Limitation
Responsible QA: Md. Mostafizur Rahman Zahid
Bug Reporting
# SL 05
issue: Post Code field accepts more than valid 4-digit Bangladesh postal code.
Reproducing Steps:
1. Goto the URL https://eticket.railway.gov.bd/ 2. Open Registration page 3. Enter more than 4 digits in Post Code field 4. Click Sign Up button
Env: Production
Module: Register
Severity: P3
Post Code Validation Error
Responsible QA: Md. Mostafizur Rahman Zahid

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (50/50)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/50)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (45/50)*100 = 90%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (5/50)*100 = 10%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/50)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A

## Recommandation
GENERAL INFORMATION
test stage | Unit performance | Functionality Regression | Integration Acceptance | System Pilot | Interface
Specify the testing stage for this test case
Date: | mm/dd/yy |  | System Date,If Applicable |  | mm/dd/yy
Tester: | Specify the name (s)of who is testing this case scenario. |  | Test Case Number |  | Specify the unique test number assigned to the test case
Test case Description: | Provide a brief description of what functionality the test case
Results: | Pass Fail |  | Incident Number,If Applicable: |  | Specify the unique identifier assingned to the incident.
INTRODUCTION
Requirement(s) to be tested: | Identify the requirments to be tested and include the requirment number and description from the Requirments Traceability Matrix
Roles and Responsibilites: | Describe each project team member and stakeholder involved in the test, and identify their associated responsibility for ensuring the test is executed appropriately
Set Up procedures: | Describe the sequence of actions necessary to prepare for execution of the test
Stop Procedures: | Describe the sequence of actions necessary to terminate the test
ENVIRONMENTAL NEEDS
Hardware: | Identify the qualities and configurations of the hardware required to execute the test case
Software: | Identify system and application software required to execute the test case.Specify any software that the test case will interact with.
Procedural Requirments: | Describe any constraints on the test procedures necessary to execute the test case
TEST
Test Items and Features: | Identify and describe the items and features that will be exercised by the test case.Group the test cases into logically related scenarios that test related items and features.For each item or feature,a reference to its associated requirment source should be include.
Input Specifications: | Define each input required to execute the test case and reference any required relationship between inputs.
Procedural Steps: | Describe the sequence of actions necessary to prepare and execute the test case.Provide detailed testprocedures for each test case; explain precisely how each test case will be executed.
Expected Results of Case: | Describe the outcome anticipated from the test case.Specify the criteria to be used to determine whether the item has passed or failed.
ACTUAL RESULTS
Output Specifications: | Define all of the outputs and features required of the test case and provided expected values. While executing the test, record and describe the visually observable outputs as they occure.Produce tangible evedence of the output such as ascreen print. At the conclusion,discreancies between the expected results and the actual results.